## Cover
Job Register — B260042
Build Number | B260042
Client Code | TFS
Client Name | Thermo Fisher Scientific
Opened
Project Mgr
RELATED DOCUMENTS & LINKS
Document / Workbook | Link / Path
Master Register
Library Register
Numbering System SOP

## Jobs
Job Register — B260042
Build: | B260042 | Client: | TFS — Thermo Fisher Scientific | Total Jobs: |  | Complete:
All Jobs for this Build ¦ Electrical: J03[####] ¦ Mechanical: J06[####] ¦ Library Ref: L[CC][####]
J03 Electrical | J06 Mechanical | J09 Hardware | J12 Supplies | J15 Made-in | J18 Assembly | J21 Item | J24 Engineering | J27 DevOps
Job Number | Category Code | Discipline | Job Type | Job Description | Assigned Tech | Start Date | Target Complete | Actual Complete | Job Status | Hours Est. | Hours Actual | Library Ref | Notes
B260042-J030001 | 03 | Electrical | Initial Build | Controls & wiring – conveyor line, 24VDC panel | J. Doe | 2026-02-05 | 2026-05-01 |  | In Progress | 160 |  | L030001
B260042-J030002 | 03 | Electrical | Revision | Vision system electrical – Station 2 integration | J. Doe | 2026-05-15 | 2026-07-30 |  | Not Started | 40 |  |  | Pending J030001 completion
B260042-J060001 | 06 | Mechanical | Initial Build | Frame fabrication & conveyor integration | J. Smith | 2026-02-05 | 2026-06-15 |  | In Progress | 280 |  | L060001
B260042-J060002 | 06 | Mechanical | Revision | Guarding installation – perimeter safety fence | J. Smith | 2026-06-20 | 2026-07-15 |  | Not Started | 60

## Library References
Library References — B260042
Library work orders referenced on this build. These are defined in the Library Register and applied here.
Library Number | Category Code | Discipline | Title / Work Order Name | Applied To (Job #) | Notes
L030001 | 03 | Electrical | Standard Electrical Commissioning Checklist | B260042-J030001
L060001 | 06 | Mechanical | Standard Mechanical Alignment & Leveling Procedure | B260042-J060001

## Number Generator
Number Generator — B260042
Use this sheet to generate Job Numbers for this build.
JOB NUMBER GENERATOR — ELECTRICAL (J03)
Build Number | B260042 | Fixed for this workbook
Next Seq # | 1 | Start at 1; increment for each additional job in this category
Generated Job # |  | e.g. B260042-J030001
JOB NUMBER GENERATOR — MECHANICAL (J06)
Build Number | B260042 | Fixed for this workbook
Next Seq # | 1
Generated Job # |  | e.g. B260042-J060001
JOB NUMBER GENERATOR — HARDWARE (J09)
Build Number | B260042 | Fixed for this workbook
Next Seq # | 1
Generated Job # |  | e.g. B260042-J090001
JOB NUMBER GENERATOR — SUPPLIES (J12)
Build Number | B260042 | Fixed for this workbook
Next Seq # | 1
Generated Job # |  | e.g. B260042-J120001
JOB NUMBER GENERATOR — MADE-IN (J15)
Build Number | B260042 | Fixed for this workbook
Next Seq # | 1
Generated Job # |  | e.g. B260042-J150001
JOB NUMBER GENERATOR — ASSEMBLY (J18)
Build Number | B260042 | Fixed for this workbook
Next Seq # | 1
Generated Job # |  | e.g. B260042-J180001
JOB NUMBER GENERATOR — ITEM (J21)
Build Number | B260042 | Fixed for this workbook
Next Seq # | 1
Generated Job # |  | e.g. B260042-J210001
JOB NUMBER GENERATOR — ENGINEERING (J24)
Build Number | B260042 | Fixed for this workbook
Next Seq # | 1
Generated Job # |  | e.g. B260042-J240001
JOB NUMBER GENERATOR — DEVOPS (J27)
Build Number | B260042 | Fixed for this workbook
Next Seq # | 1
Generated Job # |  | e.g. B260042-J270001
⚠ Job sequences restart at 0001 for each category on each new build. When a job scope is reusable, promote it to a Library entry (L03[####] or L06[####]) in the Library Register.